## Module Tracker
Ziplofy — Shopify Module Status Tracker
Report snapshot date: 22 Jun 2026 ¦ Phase 1 = launch scope ¦ Phase 2 = marketing, analytics & activity log (deferred)
Phase | Tier | Tier Name | Category | Module | Status | Completion % | Current State / Notes | Suggested Priority | Date Started | Target End Date | Date Completed | Owner | Comments | Report Date
PHASE 1 — LAUNCH SCOPE
Phase 1 | 1 | Commerce Core | Catalog & Inventory | Products & variants | Complete | 95% | Full CRUD, search, soft delete | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Catalog & Inventory | Collections | Complete | 90% | Theme templates recently added | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Catalog & Inventory | Inventory levels | Complete | 90% | Per-location management | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Catalog & Inventory | Gift cards | Complete | 85% | Admin + timeline | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Supply Chain | Purchase orders | Complete | 90% | Create, receive, tags | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Supply Chain | Transfers & shipments | Complete | 90% | Warehouse-style ops | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Supply Chain | Vendors | Complete | 85% | Vendor management operational | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Pricing & Promotions | Discounts (4 types) | Complete | 95% | Best-in-class; storefront validation | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Customers | Customers | Complete | 85% | List, detail, addresses, timeline | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Customers | Customer segments | Complete | 85% | Segment CRUD and entries | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Customers | Tag management | Complete | 90% | Product/customer/PO/transfer tags | Maintain | [5 empty] | 2026-06-22
Phase 1 | 1 | Commerce Core | Recovery | Abandoned carts (view) | Complete | 75% | List + recovery UI; automation weak | Medium | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Orders | Orders list & detail | Complete | 80% | Read-only admin | High | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Orders | Create order / drafts | Stub | 25% | UI exists; no create-order API | Critical | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Orders | Order fulfillment | Missing | 10% | No fulfill/cancel/refund/edit | Critical | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Orders | Returns & refunds | Stub | 15% | Policy text only; templates exist, no workflow | Critical | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Checkout | Storefront checkout | Partial | 50% | Creates orders; client-trusted totals | Critical | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Checkout | Checkout settings | Complete | 90% | Large settings surface | Maintain | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Payments | Manual payments (UPI/bank/COD) | Complete | 85% | Recently built | Maintain | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Payments | Payment gateways (Stripe/Razorpay) | Stub | 10% | Provider catalog; no OAuth/capture | Critical | [5 empty] | 2026-06-22
Phase 1 | 2 | Orders & Checkout | Payments | Transactions | Complete | 75% | Manual confirmations only | High | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Shipping | Shipping profiles/zones/rates | Complete | 90% | Deep configuration | Maintain | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Shipping | Local delivery | Partial | 60% | Some API wiring gaps | High | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Shipping | Order-linked shipping labels | Missing | 5% | Transfers only, not orders | High | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Tax | Taxes & duties (config) | Complete | 85% | India tax detail page ~1600 lines | Maintain | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Tax | Tax at checkout | Partial | 40% | Not recalculated server-side | Critical | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Markets | Markets | Complete | 75% | Admin CRUD | Medium | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Markets | Market catalogs | Complete | 80% | Catalog market assignments | Medium | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Markets | Multi-currency checkout | Missing | 15% | Config exists; checkout doesn't use it | High | [5 empty] | 2026-06-22
Phase 1 | 3 | Shipping, Tax & Markets | Shipping | Free shipping at checkout | Partial | 50% | Static rate TODO in backend | High | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Themes | Theme library & install | Complete | 90% | Install and manage themes | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Themes | Theme editor / code editor | Complete | 85% | In-browser theme editing | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Themes | Custom theme builder | Complete | 80% | 444-file subsystem | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Themes | Storefront SSR render | Complete | 75% | Liquid + React packs | Medium | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | Store menus | Complete | 85% | Navigation menu management | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | Files / media | Complete | 80% | S3 uploads | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | Online store pages | Stub | 20% | Hardcoded placeholders | Medium | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | Blog / articles | Stub | 15% | Placeholder HTML in render controller | Medium | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | URL redirects | Stub | 10% | Empty UI | Low | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Content | Metaobjects / metafields | Stub | 15% | Coming soon in settings | Medium | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Policies | Store policies | Complete | 85% | Terms, privacy, shipping, returns | Maintain | [5 empty] | 2026-06-22
Phase 1 | 4 | Online Store & Themes | Accounts | Customer accounts (storefront) | Partial | 55% | Auth works; social login partial | High | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Store | General settings | Complete | 85% | Core store configuration | Maintain | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Store | Branding | Complete | 85% | Logo, colors, identity | Maintain | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Access | Roles & permissions | Complete | 80% | Permission tree + API | Maintain | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Access | Users / staff | Partial | 65% | Staff management gaps | Medium | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Store | Locations | Complete | 85% | Location CRUD | Maintain | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Notifications | Notifications | Partial | 60% | Test email/toggle TODOs | Medium | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Integrations | Webhooks | Partial | 30% | Static signing key; create flow TODO | High | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Domains | Domains | Partial | 25% | Mock data | High | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Localization | Languages | Stub | 5% | Coming soon | Low | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Integrations | Apps & sales channels | Stub | 5% | Placeholder | Medium | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Billing | Plan / billing (merchant SaaS) | Partial | 45% | Membership plans hook; billing UI scaffold | High | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Privacy | Customer privacy | Partial | 50% | Privacy settings partial | Medium | [5 empty] | 2026-06-22
Phase 1 | 7 | Settings & Platform Admin | Security | API security (auth on routes) | Partial | 50% | Many admin routes lack protect | Critical | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Auth | Admin auth (OTP/JWT) | Complete | 85% | OTP + JWT authentication | Maintain | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Auth | Storefront customer auth | Complete | 80% | Customer login/register | Maintain | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Email | Email templates | Complete | 70% | Order confirm works | Medium | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Email | Email queue (BullMQ) | Missing | 10% | Disabled in index.ts | High | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Integrations | Webhooks for apps | Missing | 0% | Not implemented | High | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Integrations | App marketplace / API keys | Missing | 0% | Not implemented | Medium | [5 empty] | 2026-06-22
Phase 1 | 8 | Infrastructure & Platform | Automation | Background automation runner | Missing | 5% | Flows stored, not executed | High | [5 empty] | 2026-06-22
PHASE 2 — MARKETING, ANALYTICS & AUDIT
Phase 2 | 5 | Marketing & Growth | Marketing | Marketing overview | Partial | 40% | Presentational stats | Medium | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Marketing | Campaigns | Stub | 15% | Empty handlers | Medium | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Marketing | Attribution | Stub | 10% | Always No data | Low | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Automation | Automations (UI) | Partial | 55% | Large builder; no execution engine | High | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Tracking | Pixels / customer events | Complete | 75% | Pixel management operational | Maintain | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Merchandising | Product offers (PDP badges) | Complete | 80% | PDP badge configuration | Maintain | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Dashboard | Dashboard / home | Partial | 35% | Mock chart data | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Dashboard | Analytics page | Partial | 35% | Reuses mock dashboard | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Reports | Reports | Missing | 0% | Sidebar link; no route | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Reports | Live view | Missing | 0% | Sidebar link; no route | Medium | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Exports | Export logs | Missing | 5% | Backend route not mounted | Medium | [5 empty] | 2026-06-22
Phase 2 | 7 | Settings & Platform Admin | Audit | Activity log | Partial | 30% | Mock entries | Medium | [5 empty] | 2026-06-22

## Phase 2 Roadmap
Phase 2 Roadmap — Marketing, Analytics & Activity Log
Deferred post-launch scope. Includes all Tier 5 (Marketing & Growth), Tier 6 (Analytics & Reporting), and Activity log from Settings.
Modules in Phase 2: 12 ¦ Fill Date Started / Target End Date for Phase 2 sprint planning
Phase | Tier | Tier Name | Category | Module | Status | Completion % | Current State / Notes | Suggested Priority | Date Started | Target End Date | Date Completed | Owner | Comments | Report Date
Marketing & Growth (Tier 5)
Phase 2 | 5 | Marketing & Growth | Marketing | Marketing overview | Partial | 40% | Presentational stats | Medium | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Marketing | Campaigns | Stub | 15% | Empty handlers | Medium | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Marketing | Attribution | Stub | 10% | Always No data | Low | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Automation | Automations (UI) | Partial | 55% | Large builder; no execution engine | High | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Tracking | Pixels / customer events | Complete | 75% | Pixel management operational | Maintain | [5 empty] | 2026-06-22
Phase 2 | 5 | Marketing & Growth | Merchandising | Product offers (PDP badges) | Complete | 80% | PDP badge configuration | Maintain | [5 empty] | 2026-06-22
Analytics & Reporting (Tier 6)
Phase 2 | 6 | Analytics & Reporting | Dashboard | Dashboard / home | Partial | 35% | Mock chart data | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Dashboard | Analytics page | Partial | 35% | Reuses mock dashboard | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Reports | Reports | Missing | 0% | Sidebar link; no route | High | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Reports | Live view | Missing | 0% | Sidebar link; no route | Medium | [5 empty] | 2026-06-22
Phase 2 | 6 | Analytics & Reporting | Exports | Export logs | Missing | 5% | Backend route not mounted | Medium | [5 empty] | 2026-06-22
Audit & Compliance
Phase 2 | 7 | Settings & Platform Admin | Audit | Activity log | Partial | 30% | Mock entries | Medium | [5 empty] | 2026-06-22
Phase 2 summary | [5 empty] | 31.67% | 12 modules — avg completion at handoff

## Tier Summary
Tier Scorecard
Tier | Tier Name | Total Modules | Complete Modules | Avg Completion % | Assessment | Date Started | Target End Date | Date Completed | Owner | Comments
1 | Commerce Core | 12 | 12 | 88% | Strongest area — catalog, discounts, inventory ops
2 | Orders & Checkout | 9 | 4 | 49% | Biggest gap — fulfillment, gateways, order lifecycle
3 | Shipping, Tax & Markets | 9 | 6 | 61% | Config strong; checkout tax/currency gaps
4 | Online Store & Themes | 12 | 8 | 58% | Differentiator — theme builder strong; CMS weak
5 | Marketing & Growth | 6 | 2 | 46% | Deferred to Phase 2 — UI present; execution engine missing
6 | Analytics & Reporting | 5 | 0 | 15% | Deferred to Phase 2 — mostly mock data or missing routes
7 | Settings & Platform Admin | 14 | 5 | 52% | Core settings done; activity log deferred to Phase 2
8 | Infrastructure & Platform | 7 | 3 | 41% | Auth solid; queues, webhooks, automation missing
Overall platform assessment
The product already feels like Shopify in catalog, discounts, shipping/tax config, themes, and inventory ops. It is not yet at parity for payments, order lifecycle, fulfillment, returns, analytics, CMS, and app ecosystem.

## Platform Scale
Platform Scale Metrics
Metric | Value | Comments
Admin routes | ~120 routes in App.tsx
Admin pages | 154+ page components
React contexts | ~99 (heavy context-driven architecture)
Backend API prefixes | ~115 under /api/*
Controllers | 123
Mongoose models | 143+
Theme builder | 444+ files in create-theme/

## Legend
Status Legend
Status | Definition
Complete | End-to-end (UI + API + real data)
Partial | Works but gaps, mocks, or missing backend
Stub | UI shell / Coming soon
Missing | Not built or not routed